## JIRA Backlogs
Issue ID | User Story | Description | Story Points | Assigned Team Member | Git Branch Name | Sprint
JIRA-101 | Project Initialization | Setup Flask project structure & repo | 3 | Akshit | feature/project-setup | Sprint 1
JIRA-102 | UI Development | Create frontend UI using HTML & CSS | 5 | Rohit | feature/ui-design | Sprint 1
JIRA-103 | Model Integration | Integrate NLP translation model | 8 | Sneha | feature/nlp-model | Sprint 1
JIRA-104 | Translation API | Develop Flask API for translation | 5 | Akshit | feature/translation-api | Sprint 2
JIRA-105 | Input Validation | Handle empty and invalid inputs | 3 | Neha | feature/input-validation | Sprint 2
JIRA-106 | Performance Optimization | Optimize model loading and response time | 5 | Sneha | feature/performance | Sprint 2
JIRA-107 | Testing | Perform unit and integration testing | 5 | Rohit | feature/testing | Sprint 3
JIRA-108 | Deployment | Deploy application on Render | 8 | Akshit | release/render-deploy | Sprint 3
JIRA-109 | Documentation | Prepare SRS and README files | 3 | Neha | docs/project-docs | Sprint 3